## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
MASTER TIMETABLE GENERATOR | [6 empty] | COMPANY NAME
DR. RAHUL AMBEKAR | [6 empty] | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Days) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Suraj,Neel,Adesh | 2019-07-22 | 2019-07-26 | 5 | 100% | bar: WEEK 1 R to WEEK 2 T
1.1.1 | Research paper finalization | Suraj,Neel,Adesh | 2019-07-27 | 2019-07-27 | 1 | 100% | bar: WEEK 2 W
1.2 | Project Title | Suraj,Neel,Adesh | 2019-08-02 | 2019-08-09 | 10 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Abstract | Adesh | 2019-08-09 | 2019-08-16 | 8 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Objectives | Adesh | 2019-08-09 | 2019-08-16 | 8 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Literature Review | Neel | 2019-08-09 | 2019-08-16 | 8 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Problem Definition | Neel | 2019-08-09 | 2019-08-16 | 8 | 100% | bar: WEEK 3 F
1.7 | Scope | Adesh,Neel | 2019-08-09 | 2019-08-16 | 8 | 100% | bar: WEEK 3 F
1.8 | Technology stack | Suraj | 2019-08-17 | 2019-08-30 | 14 | 100% | bar: WEEK 3 F
1.9 | Benefits for environment | Suraj | 2019-08-09 | 2019-08-16 | 8 | 100% | bar: WEEK 3 F
1.1 | Benefits for society | Suraj | 2019-08-09 | 2019-08-16 | 8 | 100% | bar: WEEK 3 F to WEEK 4 M
1.11 | Applications | Adesh,Neel | 2019-08-09 | 2019-08-16 | 8 | 100% | bar: WEEK 3 F to WEEK 4 M
2 | Project Design
2.1 | Proposed System | Neel | 2019-08-31 | 2019-09-03 | 4 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Adesh | 2019-09-20 | 2019-09-27 | 8 | 100% | bar: WEEK 4 F to WEEK 5 F
2.3 | Activity Diagram | Suraj | 2019-09-20 | 2019-09-27 | 8 | 100%
2.4 | Use Case Diagram | Suraj | 2019-09-20 | 2019-09-27 | 8 | 100%
2.5 | Description Of Use Case | Suraj | 2019-09-20 | 2019-09-27 | 8 | 100%
2.6 | Modules | Adesh,Neel | 2019-10-15 | 2019-10-24 | 9 | 100%
2.6.1 | Department level module | Adesh,Neel | 2019-10-15 | 2019-10-24 | 9 | 100%
2.6.2 | Faculty & Resource aloocation | Adesh,Neel | 2019-10-15 | 2019-10-24 | 9 | 100%
2.6.3 | Admin Module | Adesh,Neel | 2019-10-15 | 2019-10-24 | 9 | 100%
2.6.4 | Integration of department module | Adesh,Neel | 2019-10-15 | 2019-10-24 | 9 | 100%
2.6.5 | Master Time-Table module | Adesh,Neel | 2019-10-15 | 2019-10-24 | 9 | 100%
2.7 | Preparation Of Report | Suraj,Neel | 2019-10-24 | 2019-10-30 | 16 | 100%
3 | Project Implementation
3.1 | Module-1 | X |  |  | 0 | 0%
3.2 | Module-2 | Y |  |  | 0 | 0%
3.3 | Module-3 | Y |  |  | 0 | 0%
3.4 | Module-4 | Z |  |  | 0 | 0%
4 | Testing
4.1 | Design of Test Cases | Y |  |  | 0 | 0%
4.2 | Testing | Y |  |  | 0 | 0%
5 | Results and Analysis
5.1 | Analysis Of Results | Y |  |  | 0 | 0%
5.2 | Graphical Representation | Y |  |  | 0 | 0%
5.3 | Report Preparation